# 🚀 ETL UI Hackathon - 1 Week Plan

## 🎯 Goal: Build a demo-ready MVP that showcases core value

Entity: Employee only (expandable later)
Timeline: 7 days (60-80 total hours)
Demo focus: Usability, intuitiveness, visual appeal

## 📊 MVP Feature Set (Ruthlessly Scoped)

### ✅ MUST HAVE (Core Demo)

- ✅ Upload CSV file (with drag & drop)

- ✅ Preview source data (first 10 rows)

- ✅ Select entity (Employee - hardcoded for MVP)

- ✅ Drag-and-drop field mapping (1:1 fields only)

- ✅ Smart auto-mapping (fuzzy match algorithm)

- ✅ Visual connection lines between mapped fields

- ✅ Before/After preview (side-by-side)

- ✅ Basic validation (required fields check)

- ✅ Download transformed CSV

### 🎁 NICE TO HAVE (If ahead of schedule)

- 🎁 Date format conversion (MM/DD/YYYY → YYYY-MM-DD)

- 🎁 Skills denormalization (Skill1, Skill2, Skill3 → multiple rows)

- 🎁 Validation suggestions (e.g., “Use current timestamp for LAST_ACTIVITY_TS”)

- 🎁 Save mapping configuration (LocalStorage, not database)

### ❌ OUT OF SCOPE (Post-hackathon)

- ❌ Multiple entities (just Employee for demo)

- ❌ XML export (CSV only)

- ❌ Database / User accounts

- ❌ Complex transformations (concatenate, split, etc.)

- ❌ Production deployment (run locally for demo)

## 📅 Day-by-Day Breakdown

### Day 1 (Saturday): Setup & Architecture (8 hours)

Team: All 4 developers

#### Morning (4 hours): Project Setup

- Create GitHub repo

- Set up React project (Vite + TypeScript + Tailwind CSS)

- Set up FastAPI backend

- Install dependencies:

  - Frontend: react-dnd, react-hook-form, axios, recharts

  - Backend: fastapi, pandas, openpyxl, python-multipart

- Create basic project structure

- Set up CORS, API routes

- Hello World: Frontend calls Backend API

#### Afternoon (4 hours): Core Components

- Dev 1: File upload component (drag & drop)

- Dev 2: Data table preview component

- Dev 3: Backend: File parser (CSV/Excel → JSON)

- Dev 4: Hardcoded Employee schema (JSON format)

Deliverable: Can upload file and see data preview

### Day 2 (Sunday): Field Mapping UI (8 hours)

Focus: Build the drag-and-drop interface

#### Dev 1 & 2: Frontend (8 hours)

- Implement React DnD

- Source fields panel (left side)

- Target fields panel (right side)

- Drag source field → Drop on target field

- Show mapping indicator (✅ mapped, ❌ not mapped)

- Basic styling (make it look good!)

#### Dev 3 & 4: Backend + Schema (8 hours)

- Employee schema with field definitions

- API endpoint: GET /api/schema/employee

- API endpoint: POST /api/mapping/validate

- Field type definitions (string, date, email, etc.)

Deliverable: Can drag fields and see mappings

### Day 3 (Monday): Auto-Mapping Algorithm (6 hours)

Focus: Smart field matching

#### Dev 1: Auto-Mapping UI (3 hours)

- “Auto-Map” button

- Show confidence scores for each mapping

- “Accept All” / “Accept Selected” buttons

- Highlight auto-mapped fields in different color

#### Dev 2: Fuzzy Matching (3 hours)

- Implement Levenshtein distance algorithm

- Common alias dictionary:

- {
  'empid': 'EMPLOYEE_ID',
  'firstname': 'FIRST_NAME',
  'lastname': 'LAST_NAME',
  'hiredate': 'HIRING_DATE',
  'email': 'EMAIL',
  # ... more
}

- API endpoint: POST /api/mapping/auto-suggest

#### Dev 3: Transformation Engine (3 hours)

- Basic 1:1 field mapping

- Create target DataFrame from mapping config

- API endpoint: POST /api/transform/preview

#### Dev 4: Testing + Bug Fixes (3 hours)

- Test with sample data

- Fix any issues

- Prepare test datasets

Deliverable: Auto-mapping works, suggests field mappings

### Day 4 (Tuesday): Visual Connection Lines (6 hours)

Focus: Make it visually stunning

#### Dev 1 & 2: Visual Lines (6 hours)

- Use SVG or Canvas to draw lines

- Animate lines when mapping changes

- Color-code lines:

  - 🟢 Green = High confidence (>0.9)

  - 🟡 Yellow = Medium confidence (0.7-0.9)

  - 🔴 Red = Low confidence (<0.7)

  - ⚪ Gray = Manual mapping

- Hover effects (highlight line on hover)

- Click line to edit mapping

#### Dev 3: Backend Optimization (3 hours)

- Optimize transformation logic

- Add response caching

- Error handling

#### Dev 4: Sample Data Preparation (3 hours)

- Create 3 sample customer files:

  - Workday format

  - SuccessFactors format

  - Oracle HCM format

- Different field names, date formats, etc.

- Shows versatility of tool

Deliverable: Beautiful visual UI with animated lines

### Day 5 (Wednesday): Preview & Validation (6 hours)

Focus: Before/After comparison

#### Dev 1: Preview UI (3 hours)

- Side-by-side comparison

- Before: Source data (first 10 rows)

- After: Transformed data (first 10 rows)

- Show transformation summary:

  - “3 rows → 3 rows (EMPLOYEE-MAIN.csv)”

  - “Required fields: 5/6 mapped (83%)”

  - “Optional fields: 3/10 mapped”

#### Dev 2: Validation UI (3 hours)

- Validation panel

- Show errors (🔴), warnings (⚠️), info (ℹ️)

- Click error to jump to field

- Suggestion actions:

  - “Use current timestamp for LAST_ACTIVITY_TS”

  - “Map Phone to PHONE field”

#### Dev 3: Validation Logic (3 hours)

- Required field validation

- Date format validation (regex check)

- Email format validation

- API endpoint: POST /api/validate

#### Dev 4: Backend Testing (3 hours)

- Integration testing

- Edge case handling

- Performance testing with larger files

Deliverable: Complete preview and validation flow

### Day 6 (Thursday): Polish & Bonus Features (6 hours)

Focus: Make it demo-ready

#### Morning (3 hours): Core Polish

- Dev 1: Responsive design, mobile-friendly

- Dev 2: Loading states, progress indicators

- Dev 3: Export CSV functionality

- Dev 4: Error handling, user feedback

#### Afternoon (3 hours): Bonus Features (Pick 1-2)

Option A: Date Format Conversion (Easier, 2 hours) - [ ] Detect date format in source - [ ] Show transformation: “10/30/2020 → 2020-10-30” - [ ] Visual indicator in preview

Option B: Skills Denormalization (Medium, 3 hours) - [ ] Detect multi-column pattern (Skill1, Skill2, Skill3) - [ ] Suggest denormalization - [ ] Show preview: “1 row → 3 rows”

Option C: Save Configuration (Easy, 1 hour) - [ ] Save mapping to LocalStorage - [ ] Load saved mapping - [ ] List of recent mappings

Choose based on what judges will find most impressive!

Deliverable: Polished, demo-ready application

### Day 7 (Friday): Demo Prep & Testing (6 hours)

Focus: Nail the presentation

#### Morning (3 hours): Final Testing

- End-to-end testing with all 3 sample files

- Fix critical bugs

- Performance testing

- Browser compatibility (Chrome, Firefox)

- Record demo video (backup in case of technical issues)

#### Afternoon (3 hours): Demo Preparation

- Create demo script (5-minute walkthrough)

- Prepare talking points:

  - Problem statement (2 min)

  - Solution demo (5 min)

  - Technical highlights (2 min)

  - Future roadmap (1 min)

- Prepare backup slides (in case demo fails)

- Test presentation setup

- Deploy to local server or cloud (Vercel/Railway)

Demo Script Structure:

1. Problem (30 sec): "HR teams spend days filling complex CSV templates..."
2. Solution (30 sec): "We built a drag-and-drop tool that does it in minutes"
3. Demo (4 min):
   - Upload messy customer file
   - Click "Auto-Map" (wow moment #1)
   - Show visual connection lines (wow moment #2)
   - Preview before/after (wow moment #3)
   - Download transformed file
4. Value (30 sec): "Reduces implementation time by 70%"
5. Q&A (remaining time)

Deliverable: Polished demo, confident team

## 🏗️ Technical Architecture (Simplified for Hackathon)

### Frontend Stack

React 18 + TypeScript
Vite (faster than Create React App)
Tailwind CSS (rapid styling)
React DnD or dnd-kit (drag & drop)
Axios (API calls)

### Backend Stack

FastAPI (Python)
Pandas (data transformation)
No database (keep it simple!)

### Project Structure

hackathon-etl/
├── frontend/
│   ├── src/
│   │   ├── components/
│   │   │   ├── FileUpload.tsx
│   │   │   ├── DataPreview.tsx
│   │   │   ├── FieldMapping.tsx
│   │   │   ├── ConnectionLines.tsx
│   │   │   ├── TransformPreview.tsx
│   │   │   └── ValidationPanel.tsx
│   │   ├── hooks/
│   │   │   └── useMapping.ts
│   │   ├── services/
│   │   │   └── api.ts
│   │   └── App.tsx
│   └── package.json
├── backend/
│   ├── main.py
│   ├── schema.py (Employee schema)
│   ├── mapper.py (Auto-mapping logic)
│   ├── transformer.py (Data transformation)
│   ├── validator.py (Validation logic)
│   └── requirements.txt
└── sample_data/
    ├── workday_export.csv
    ├── successfactors_export.csv
    └── oracle_hcm_export.csv

## 🎨 UI Design Priorities (For Judges)

### 1. First Impression (10 seconds)

- Clean, modern design (Tailwind + gradients)

- Clear call-to-action: “Upload Your Employee Data”

- Professional color scheme:

  - Primary: #6366f1 (Indigo)

  - Success: #10b981 (Green)

  - Warning: #f59e0b (Amber)

  - Error: #ef4444 (Red)

### 2. Intuitive Flow (30 seconds)

- Progress stepper at top: [1] Upload → [2] Map → [3] Preview → [4] Download

- Obvious next actions: Big buttons with icons

- Minimal text, maximum clarity

### 3. Visual Feedback (Constantly)

- Loading states (spinners, skeleton screens)

- Success animations (checkmarks, confetti)

- Smooth transitions (fade in/out, slide)

- Hover effects (tooltips, highlights)

### 4. “Wow” Moments

- Moment 1: Auto-map finds 8/10 fields instantly

- Moment 2: Lines animate connecting fields

- Moment 3: Preview updates in real-time

- Moment 4: Download happens with success message

## 📝 Critical Success Factors

### DO’s ✅

- ✅ Focus on UI/UX: Judges prioritize usability over technical complexity

- ✅ Use Cursor aggressively: Let AI write boilerplate, components, styling

- ✅ Test early, test often: Don’t wait until Day 6 to test

- ✅ Commit frequently: Push to GitHub every few hours

- ✅ Communicate: Daily standup (15 min sync each day)

- ✅ Have fun: Hackathons are about learning and creativity!

### DON’Ts ❌

- ❌ Don’t over-engineer: No microservices, no Kubernetes, no OAuth

- ❌ Don’t add features mid-week: Stick to the plan

- ❌ Don’t skip testing: A buggy demo loses points

- ❌ Don’t work in isolation: Integrate frequently

- ❌ Don’t sacrifice sleep: Work smart, not exhausted

## 🔥 Cursor AI Acceleration Tips

### Use Cursor For:

- Component Generation:

- Prompt: "Create a React component FileUpload with drag-and-drop, 
        using Tailwind CSS, showing upload progress"

- API Endpoints:

- Prompt: "Create FastAPI endpoint to parse uploaded CSV file, 
        return first 10 rows as JSON, handle errors"

- Fuzzy Matching:

- Prompt: "Implement Levenshtein distance algorithm in Python, 
        find closest match between two string lists"

- Styling:

- Prompt: "Add Tailwind classes to make this form beautiful, 
        modern, with smooth animations and hover effects"

- Bug Fixing:

- Prompt: "This component is not re-rendering when state changes. 
        Fix the React hooks issue."

### Cursor Workflow:

1. Write high-level comment describing what you need
2. Let Cursor generate the code
3. Review and adjust
4. Test immediately
5. Iterate if needed

Time savings: ~50% faster than writing from scratch

## 🎯 Demo Day Checklist

### Day Before Demo:

- Full end-to-end test with all sample files

- Record backup demo video

- Prepare 3-5 slides (problem, solution, demo, roadmap)

- Test on demo laptop/setup

- Charge all devices

- Sleep well!

### Demo Day Morning:

- Arrive early to set up

- Test internet connection

- Have backup: Run demo locally if WiFi fails

- Clear browser cache, close unnecessary tabs

- Run demo once to warm up

### During Demo (5-10 min):

- Start with the problem (relatable story)

- Show the “before” (customer pain)

- Demo the solution (wow them!)

- Highlight key innovations:

  - Smart auto-mapping (AI-powered)

  - Visual connection lines (intuitive)

  - Real-time preview (confidence-building)

- End with impact: “Reduces time from weeks to minutes”

- Be ready for Q&A

## 📊 Judging Criteria Strategy

### Usability (35 points) - PRIORITIZE THIS

- ✅ Can non-technical user complete task without help?

- ✅ Clear, obvious next actions

- ✅ Minimal clicks to achieve goal

- ✅ Error messages are helpful, not cryptic

Strategy: Focus all polish on Days 5-6 here

### Simplicity (25 points)

- ✅ UI is not cluttered

- ✅ Only essential features visible

- ✅ Advanced features hidden (if implemented)

Strategy: Remove everything non-essential

### User-Friendliness (25 points)

- ✅ Looks professional (good design)

- ✅ Feels responsive (fast interactions)

- ✅ Provides feedback (loading, success, errors)

Strategy: Animations, loading states, visual feedback

### Intuitiveness (15 points)

- ✅ First-time users understand immediately

- ✅ No manual/documentation needed

- ✅ Follows common UI patterns

Strategy: Test with someone who’s never seen it before

## 🏆 Winning the Hackathon

### What Judges Will Love:

- 🎯 Solves a real problem: HR teams will relate immediately

- 🎨 Beautiful UI: First impression matters

- ⚡ Fast and smooth: No lag, instant feedback

- 🤖 Smart automation: Auto-mapping feels like magic

- 🎭 Great demo: Confident, clear, memorable

### Secret Sauce:

- Story: Start with a relatable customer pain story

- Contrast: Show “before” (manual, tedious) vs “after” (automated, easy)

- Magic moment: The auto-map button click that finds all fields

- Confidence: “We tested this with 3 different HR systems”

- Vision: “This is just Employee - we can do Candidate, Role, etc.”

## 💡 Emergency Pivots (If Behind Schedule)

### If Day 3 and struggling:

- Skip auto-mapping, focus on manual drag-and-drop only

- Skip visual lines, use simple list view

- Focus on core: Upload → Map → Preview → Download

### If Day 5 and major bugs:

- Simplify validation (just required fields)

- Skip bonus features completely

- Focus on demo-ready stability

### If Demo Day and disaster:

- Use recorded video backup

- Have slides ready to explain what it “would” do

- Emphasize the idea and potential value

## 📞 Daily Standup Questions (15 min)

Every day at 6 PM: 1. What did you complete today? 2. What will you work on tomorrow? 3. Any blockers or issues? 4. Do you need help from anyone?

Keep it short, stay aligned!

## 🎉 Post-Hackathon (If you win/want to continue)

### Week 2+: Make it Production-Ready

- Add database (PostgreSQL)

- Add more entities (Candidate, Role, Position)

- Add authentication (OAuth)

- Add XML export

- Add complex transformations

- Deploy to cloud (AWS/Azure)

- Create comprehensive documentation

## 🚀 Final Pep Talk

YES, you can absolutely do this in 1 week!

Why you’ll succeed: 1. ✅ Focused scope: Employee entity only, core features only 2. ✅ Smart tools: Cursor AI will 2-3x your speed 3. ✅ Clear plan: Follow this day-by-day breakdown 4. ✅ Great idea: Solves a real, painful problem 5. ✅ Strong team: 4 developers = parallel work

Remember: - 🎯 Quality > Quantity: Better to have 3 features that work perfectly than 10 that are buggy - 🎨 UI > Complexity: Judges care more about how it looks/feels than technical architecture - 🎭 Demo > Code: A great demo of a simple solution beats a poor demo of a complex solution - 🤝 Team > Individual: Help each other, integrate often, celebrate wins

You got this! 🚀

Good luck with your hackathon!

Questions before you start? Need help with specific implementation details? Just ask!

I’ll be here to help you build, debug, and demo! 💪