# 🔧 Modular Development Plan - 4 Independent Developers

## 🎯 Goal: Each Developer Works Independently, Integrates at Checkpoints

## 📦 Module Breakdown

### Overview:

┌─────────────────────────────────────────────────────────────┐
│                    USER INTERFACE (Browser)                  │
├─────────────────────────────────────────────────────────────┤
│                                                              │
│  ┌──────────────────┐              ┌──────────────────┐    │
│  │   MODULE 1       │              │   MODULE 2       │    │
│  │  Frontend Core   │◄────────────►│  Mapping Engine  │    │
│  │  (Dev 1)         │   React      │  (Dev 2)         │    │
│  │                  │   Context    │                  │    │
│  └──────────────────┘              └──────────────────┘    │
│           ▲                                  ▲               │
│           │                                  │               │
│           │         HTTP/JSON APIs           │               │
│           ▼                                  ▼               │
│  ┌──────────────────┐              ┌──────────────────┐    │
│  │   MODULE 3       │◄────────────►│   MODULE 4       │    │
│  │  Transform &     │   Python     │  Schema & Config │    │
│  │  Validate        │   Functions  │  (Dev 4)         │    │
│  │  (Dev 3)         │              │                  │    │
│  └──────────────────┘              └──────────────────┘    │
│                                                              │
└─────────────────────────────────────────────────────────────┘

## 👤 Module 1: Frontend Core UI

### Owner: Developer 1

### Responsibility: Upload, Preview, Export, Overall UI Shell

### What You Build:

├── App.tsx (main app shell)
├── components/
│   ├── FileUpload.tsx ⭐
│   ├── DataPreview.tsx ⭐
│   ├── ExportDownload.tsx ⭐
│   ├── Layout.tsx (header, footer, navigation)
│   ├── ProgressStepper.tsx (shows current step)
│   └── common/ (buttons, cards, modals)
├── services/
│   └── api.ts (API client wrapper)
└── App.css / tailwind config

### API Dependencies:

// You CONSUME these APIs (built by others):
POST /api/upload              // Module 3
GET  /api/schema/employee     // Module 4
POST /api/transform/export    // Module 3

### What You PROVIDE to Others:

// React Context for sharing state
export const AppContext = {
  uploadedFile: FileData,
  schema: SchemaData,
  mappings: MappingConfig,
  setMappings: (mappings) => void
}

// Reusable UI components
export { Button, Card, Modal, Toast }

### Daily Deliverables:

- Day 1: FileUpload component + API client setup

- Day 2: DataPreview component + Layout

- Day 3: API integration tests (with mocked APIs)

- Day 4: ExportDownload component

- Day 5: UI polish, loading states

- Day 6: Error handling, responsive design

- Day 7: Final testing, bug fixes

### Mock Data for Independent Work:

// Use this while Dev 3/4 build APIs
const MOCK_UPLOAD_RESPONSE = {
  filename: "workday_export.csv",
  row_count: 150,
  column_count: 12,
  columns: ["EmpID", "FirstName", "LastName", ...],
  sample_data: [
    { EmpID: "E001", FirstName: "John", LastName: "Doe", ... }
  ]
};

const MOCK_SCHEMA = {
  entity: "employee",
  fields: [
    { name: "EMPLOYEE_ID", required: true, type: "string" },
    { name: "FIRST_NAME", required: true, type: "string" },
    ...
  ]
};

### Integration Checkpoints:

- ✅ Day 2 EOD: Share AppContext and UI components with Dev 2

- ✅ Day 3 EOD: Test real API calls with Dev 3 & 4

- ✅ Day 5 EOD: Full integration test

## 🎨 Module 2: Field Mapping Engine

### Owner: Developer 2

### Responsibility: Drag-and-Drop, Visual Lines, Auto-Map UI

### What You Build:

├── components/
│   ├── FieldMapping.tsx ⭐ (main component)
│   ├── SourceFieldList.tsx
│   ├── TargetFieldList.tsx
│   ├── DraggableField.tsx
│   ├── DroppableField.tsx
│   ├── ConnectionLines.tsx ⭐ (SVG lines)
│   ├── AutoMapButton.tsx
│   └── ValidationPanel.tsx
├── hooks/
│   ├── useDragDrop.ts
│   ├── useMapping.ts
│   └── useAutoMap.ts
└── utils/
    └── lineCalculations.ts (SVG coordinate math)

### API Dependencies:

// You CONSUME these APIs:
POST /api/auto-map            // Module 4
POST /api/transform/preview   // Module 3
POST /api/validate            // Module 3

### What You CONSUME from Others:

// From Module 1 (Dev 1):
import { AppContext } from '../App';
import { Button, Card } from '../components/common';

// From AppContext:
const { uploadedFile, schema, mappings, setMappings } = useContext(AppContext);

### What You PROVIDE to Others:

// Mapping configuration format
export interface MappingConfig {
  mappings: Array<{
    source: string,
    target: string,
    confidence: number,
    method: 'exact' | 'fuzzy' | 'manual'
  }>,
  validations: ValidationResult[]
}

// Hook for other components
export const useMapping = () => {
  // Returns current mappings and setters
};

### Daily Deliverables:

- Day 1: Basic drag-and-drop setup (React DnD)

- Day 2: SourceFieldList + TargetFieldList components ⭐

- Day 3: ConnectionLines component (SVG) ⭐

- Day 4: Auto-map button + API integration

- Day 5: ValidationPanel component

- Day 6: Animations, polish, edge cases

- Day 7: Testing, bug fixes

### Mock Data for Independent Work:

// Use while Dev 4 builds auto-map API
const MOCK_AUTO_MAP_RESPONSE = {
  mappings: [
    { source: "EmpID", target: "EMPLOYEE_ID", confidence: 1.0, method: "exact" },
    { source: "FirstName", target: "FIRST_NAME", confidence: 0.95, method: "fuzzy" },
    ...
  ],
  total_mapped: 8,
  total_source: 10,
  mapping_percentage: 80
};

### Integration Checkpoints:

- ✅ Day 1 EOD: Share mapping data structure with Dev 1 & 3

- ✅ Day 3 EOD: Test with real auto-map API (Dev 4)

- ✅ Day 4 EOD: Test with real validation API (Dev 3)

- ✅ Day 5 EOD: Full integration test

## 🔧 Module 3: Transformation & Validation Engine

### Owner: Developer 3

### Responsibility: Backend APIs for Transform, Validate, Export

### What You Build:

backend/
├── main.py (FastAPI app)
├── transformer.py ⭐
│   └── class TransformationEngine
├── validator.py ⭐
│   └── class ValidationEngine
├── exporter.py
│   └── class CSVExporter
├── utils/
│   ├── date_converter.py
│   ├── field_transformer.py
│   └── denormalizer.py (if time permits)
└── tests/
    └── test_transformer.py

### APIs You BUILD:

@app.post("/api/upload")
async def upload_file(file: UploadFile):
    """Parse CSV/Excel, return preview"""
    # Your implementation
    
@app.post("/api/transform/preview")
async def preview_transformation(data: TransformRequest):
    """Apply mappings, return sample transformed data"""
    # Your implementation

@app.post("/api/validate")
async def validate_data(data: ValidationRequest):
    """Validate against schema, return errors/warnings"""
    # Your implementation
    
@app.post("/api/transform/export")
async def export_csv(data: ExportRequest):
    """Generate final CSV file for download"""
    # Your implementation

### What You CONSUME from Others:

# From Module 4 (Dev 4):
from schema_manager import get_employee_schema, ValidationRules

### What You PROVIDE to Others:

# API Response Formats (document these!)
class TransformResponse:
    transformed_data: List[dict]
    row_count: int
    transformations_applied: List[str]

class ValidationResponse:
    errors: List[ValidationError]
    warnings: List[ValidationWarning]
    is_valid: bool

### Daily Deliverables:

- Day 1: FastAPI setup + /upload endpoint ⭐

- Day 2: TransformationEngine class (basic 1:1 mapping)

- Day 3: /transform/preview endpoint ⭐

- Day 4: ValidationEngine class + /validate endpoint

- Day 5: /export endpoint + date transformations

- Day 6: Error handling, edge cases

- Day 7: Performance optimization, testing

### Mock Data for Independent Work:

# Use while Dev 4 builds schema
MOCK_SCHEMA = {
    "fields": [
        {"name": "EMPLOYEE_ID", "type": "string", "required": True},
        {"name": "FIRST_NAME", "type": "string", "required": True},
        # ...
    ]
}

# Mock validation rules
MOCK_VALIDATION_RULES = {
    "EMPLOYEE_ID": {"pattern": r"^[A-Z0-9]+$", "max_length": 50},
    "HIRING_DATE": {"format": "YYYY-MM-DD"}
}

### Integration Checkpoints:

- ✅ Day 1 EOD: /upload API working, test with Dev 1

- ✅ Day 3 EOD: /transform/preview working, test with Dev 2

- ✅ Day 4 EOD: Share transformation response format with Dev 1

- ✅ Day 5 EOD: Full integration test

## 📋 Module 4: Schema & Auto-Mapping

### Owner: Developer 4

### Responsibility: Schema Management, Auto-Map Algorithm, Configuration

### What You Build:

backend/
├── schema_manager.py ⭐
│   └── class SchemaManager
├── field_mapper.py ⭐
│   └── class FieldMapper (fuzzy matching)
├── config_manager.py
│   └── Save/load mapping configs
├── schemas/
│   └── employee_schema.json (hardcoded for MVP)
└── tests/
    └── test_field_mapper.py

### APIs You BUILD:

@app.get("/api/schema/employee")
async def get_employee_schema():
    """Return Employee entity schema"""
    # Your implementation

@app.post("/api/auto-map")
async def auto_map_fields(data: AutoMapRequest):
    """Smart field mapping with fuzzy match"""
    # Your implementation ⭐ (This is your KEY feature!)

@app.get("/api/validation-rules/employee")
async def get_validation_rules():
    """Return validation rules for Employee"""
    # Your implementation

@app.post("/api/config/save")
async def save_mapping_config(data: ConfigSaveRequest):
    """Save mapping configuration (optional)"""
    # Your implementation

### What You PROVIDE to Others:

# Schema format (document this!)
class FieldDefinition:
    name: str
    display_name: str
    type: str  # 'string', 'date', 'email', etc.
    required: bool
    max_length: Optional[int]
    pattern: Optional[str]
    example: str

class EntitySchema:
    entity_name: str
    fields: List[FieldDefinition]

# Auto-mapping response format
class AutoMapResponse:
    mappings: List[Mapping]
    total_mapped: int
    total_source: int
    mapping_percentage: float

### Daily Deliverables:

- Day 1: Employee schema JSON + /schema/employee endpoint ⭐

- Day 2: FieldMapper class with fuzzy matching ⭐

- Day 3: /auto-map endpoint (this is KEY!) ⭐

- Day 4: Alias dictionary, improve matching accuracy

- Day 5: Validation rules + /validation-rules endpoint

- Day 6: Config save/load (if time permits)

- Day 7: Testing, accuracy improvements

### Mock Data for Independent Work:

# Source fields for testing auto-map
TEST_SOURCE_FIELDS = [
    "EmpID", "FirstName", "LastName", "Email", 
    "HireDate", "JobTitle", "Department"
]

# Test your algorithm locally
def test_auto_map():
    mapper = FieldMapper()
    mappings = mapper.auto_map(TEST_SOURCE_FIELDS, EMPLOYEE_SCHEMA)
    assert len(mappings) >= 5  # Should map at least 5 fields
    assert mappings[0]['confidence'] >= 0.8

### Integration Checkpoints:

- ✅ Day 1 EOD: Share schema format with Dev 1, 2, 3

- ✅ Day 2 EOD: Share auto-map algorithm output format

- ✅ Day 3 EOD: /auto-map API working, test with Dev 2

- ✅ Day 5 EOD: Full integration test

## 🤝 Integration Strategy

### Phase 1: API Contracts (Day 0 - Setup Day)

All Devs Meet (1 hour): 1. ✅ Agree on API request/response formats 2. ✅ Document in shared file: API_CONTRACTS.md 3. ✅ Create TypeScript interfaces (Frontend) 4. ✅ Create Pydantic models (Backend)

Example API Contract:

// API_CONTRACTS.md

// POST /api/upload
interface UploadResponse {
  filename: string;
  row_count: number;
  column_count: number;
  columns: string[];
  sample_data: Record<string, any>[];
  data_types: Record<string, string>;
}

// POST /api/auto-map
interface AutoMapRequest {
  source_fields: string[];
  target_fields: FieldDefinition[];
}

interface AutoMapResponse {
  mappings: Mapping[];
  total_mapped: number;
  total_source: number;
  mapping_percentage: number;
}

// ... document ALL APIs

### Phase 2: Independent Development (Day 1-2)

Each Dev Works Solo: - ✅ Use mock data (provided above) - ✅ Build your module independently - ✅ Test with mocked dependencies - ✅ Commit code daily to separate branches

Git Workflow:

# Each dev has their own branch
git checkout -b dev1-frontend-core
git checkout -b dev2-mapping-engine
git checkout -b dev3-transformation
git checkout -b dev4-schema-automapping

# Work independently, commit often
git add .
git commit -m "Day 1: FileUpload component complete"
git push origin dev1-frontend-core

### Phase 3: First Integration (Day 3 - Midpoint)

Integration Checkpoint (2 hours):

- Backend Integration (Dev 3 + Dev 4):

- # Merge backend branches
git checkout main
git merge dev3-transformation
git merge dev4-schema-automapping
# Resolve conflicts
# Test: Backend works standalone

- Frontend Integration (Dev 1 + Dev 2):

- # Merge frontend branches
git checkout main
git merge dev1-frontend-core
git merge dev2-mapping-engine
# Resolve conflicts
# Test: Frontend works with mocked APIs

- End-to-End Test (All devs):

- # Start backend
cd backend && uvicorn main:app --reload

# Start frontend
cd frontend && npm run dev

# Test flow:
# Upload → Auto-map → Preview
# ✅ Fix any issues together

Expected Issues & Solutions: - Issue: API response doesn’t match frontend expectation - Fix: Update API_CONTRACTS.md, adjust code - Issue: CORS errors - Fix: Dev 3 updates FastAPI CORS settings - Issue: Component props don’t match - Fix: Dev 1 & 2 align on interface

### Phase 4: Continuous Integration (Day 4-6)

Daily Merge & Test (30 min each evening):

# At 6 PM daily:
# 1. Each dev commits their work
git add .
git commit -m "Day 4: Validation component complete"
git push

# 2. Merge to main (one person drives, all watch)
git checkout main
git pull
git merge dev1-frontend-core
git merge dev2-mapping-engine
git merge dev3-transformation
git merge dev4-schema-automapping

# 3. Quick integration test
# 4. Fix critical issues together (30 min max)
# 5. Everyone pulls latest main
git checkout dev1-frontend-core
git merge main

### Phase 5: Final Integration (Day 7)

Full Day Dedicated to Integration:

Morning (3 hours): - ✅ Merge all branches - ✅ Resolve conflicts - ✅ End-to-end testing - ✅ Fix critical bugs

Afternoon (3 hours): - ✅ Demo preparation - ✅ Practice demo 3-4 times - ✅ Record backup video - ✅ Prepare slides

## 📅 Daily Standup Format (15 min at 6 PM)

Each dev answers 3 questions:

### Template:

Developer: [Name]
Module: [Module 1/2/3/4]

Yesterday:
  ✅ Completed: [What you finished]
  📊 Progress: [% of your module done]

Today:
  🎯 Goal: [What you'll finish today]
  ⏰ Hours spent: [Actual time]

Blockers:
  🚧 [Any issues blocking you]
  🤝 [Need help from who?]

Integration:
  🔗 [Ready to integrate with others?]
  📤 [What you're providing to others]
  📥 [What you need from others]

### Example Standup (Day 2):

Dev 1 (Frontend Core):

Yesterday:
  ✅ Completed: FileUpload component with drag-and-drop
  📊 Progress: 30% of my module done

Today:
  🎯 Goal: Finish DataPreview component
  ⏰ Hours spent: 6 hours

Blockers:
  🚧 None

Integration:
  🔗 Ready to share: UI components library
  📤 Providing: Button, Card, Modal components to Dev 2
  📥 Need: API contract confirmation from Dev 3

Dev 2 (Mapping Engine):

Yesterday:
  ✅ Completed: Basic drag-and-drop setup
  📊 Progress: 25% of my module done

Today:
  🎯 Goal: SourceFieldList and TargetFieldList components
  ⏰ Hours spent: 8 hours

Blockers:
  🚧 None, using mocked data

Integration:
  🔗 Ready to share: Mapping data structure
  📤 Providing: MappingConfig interface to Dev 1 & 3
  📥 Need: UI components from Dev 1 (by EOD)

Dev 3 (Transformation):

Yesterday:
  ✅ Completed: FastAPI setup + /upload endpoint
  📊 Progress: 30% of my module done

Today:
  🎯 Goal: TransformationEngine class
  ⏰ Hours spent: 6 hours

Blockers:
  🚧 None, using mocked schema

Integration:
  🔗 Ready for first test: /upload API
  📤 Providing: Upload API ready for Dev 1 to test
  📥 Need: Schema format from Dev 4 (by tomorrow)

Dev 4 (Schema & Auto-Map):

Yesterday:
  ✅ Completed: Employee schema JSON
  📊 Progress: 25% of my module done

Today:
  🎯 Goal: FieldMapper class with fuzzy matching
  ⏰ Hours spent: 8 hours

Blockers:
  🚧 None

Integration:
  🔗 Ready to share: Schema format
  📤 Providing: employee_schema.json to Dev 3
  📥 Need: Nothing today, working independently

## 🎯 Clear Ownership & Responsibility

### Who Owns What:

| Component | Owner | Backup |
| --- | --- | --- |
| FileUpload | Dev 1 | Dev 2 |
| DataPreview | Dev 1 | Dev 2 |
| FieldMapping | Dev 2 | Dev 1 |
| ConnectionLines | Dev 2 | Dev 1 |
| TransformEngine | Dev 3 | Dev 4 |
| Validation | Dev 3 | Dev 4 |
| Schema | Dev 4 | Dev 3 |
| Auto-Map | Dev 4 | Dev 3 |
| API Client | Dev 1 | Dev 2 |
| FastAPI Setup | Dev 3 | Dev 4 |

### Decision Making:

- Your module: You decide (autonomy!)

- Integration: Discuss with affected devs

- Architecture: Team decision (in standup)

- Emergency: Team lead decides

## 📊 Progress Tracking

### Shared Progress Document (Google Sheet or Notion):

Day | Dev 1 | Dev 2 | Dev 3 | Dev 4 | Integration | Blockers
----|-------|-------|-------|-------|-------------|----------
1   | 30%   | 25%   | 30%   | 25%   | APIs defined | None
2   | 50%   | 50%   | 50%   | 50%   | Mock data    | None
3   | 70%   | 70%   | 70%   | 70%   | ✅ First test | CORS issue (fixed)
4   | 85%   | 85%   | 85%   | 85%   | Daily merge  | None
5   | 95%   | 95%   | 95%   | 95%   | Daily merge  | None
6   | 100%  | 100%  | 100%  | 100%  | Daily merge  | None
7   | Polish| Polish| Polish| Polish| ✅ Full test | None

## 🚨 Handling Blockers

### If You’re Blocked:

- Try for 30 min: Google, Stack Overflow, Cursor AI

- Ask in chat: Post specific question with code snippet

- Pair program: Screen share with relevant dev (15 min max)

- Escalate: If blocking progress > 1 hour, bring to standup

### Common Blockers & Solutions:

| Blocker | Solution | Who Helps |
| --- | --- | --- |
| API not ready | Use mock data | Self |
| API format mismatch | Update API_CONTRACTS.md | Affected devs |
| Component not available | Build temporarily, replace later | Self |
| Git conflict | Pair with conflicting dev | Both |
| Bug in other module | Create GitHub issue, assign | Module owner |
| Don’t understand requirement | Check specs doc, ask in chat | Team lead |

## 📦 Deliverables by Module

### End of Week, Each Dev Delivers:

Dev 1: - ✅ FileUpload component (working) - ✅ DataPreview component (working) - ✅ ExportDownload component (working) - ✅ UI component library (buttons, cards, modals) - ✅ API client wrapper - ✅ Responsive layout

Dev 2: - ✅ FieldMapping component (working) - ✅ Drag-and-drop functionality - ✅ ConnectionLines (SVG) with animations - ✅ Auto-map button integration - ✅ ValidationPanel component - ✅ Mapping state management

Dev 3: - ✅ /upload API (working) - ✅ /transform/preview API (working) - ✅ /validate API (working) - ✅ /export API (working) - ✅ TransformationEngine class - ✅ ValidationEngine class - ✅ Date format conversion

Dev 4: - ✅ /schema/employee API (working) - ✅ /auto-map API (working) ⭐ - ✅ FieldMapper with 80%+ accuracy - ✅ Alias dictionary (50+ aliases) - ✅ Validation rules definition - ✅ Schema documentation

## ✅ Success Criteria for Modular Development

Your modular approach is successful if:

- ✅ Independence: Each dev works 80% independently

- ✅ No Waiting: No one blocked for > 1 hour

- ✅ Clean Interfaces: APIs work on first integration attempt

- ✅ Git Clean: < 10 merge conflicts per day

- ✅ On Time: 90% of daily goals met

- ✅ Working Demo: Full flow works by Day 6 EOD

## 🎯 Final Checklist

### Day 0 (Before Starting):

- All devs read Module responsibilities

- Create API_CONTRACTS.md

- Set up Git branches

- Create shared progress tracker

- Schedule daily standups (6 PM)

### During Development (Days 1-6):

- Daily commits to own branch

- Daily standup at 6 PM

- Update progress tracker

- Use mock data when needed

- Ask for help when blocked > 30 min

### Integration Days (Days 3, 5, 7):

- Merge branches

- Resolve conflicts

- Integration testing

- Fix critical bugs

- Update API_CONTRACTS.md if needed

### Day 7:

- All modules working independently

- Full integration complete

- End-to-end test passes

- Demo ready

- Backup video recorded

## 🎉 Why This Works

### Benefits of Modular Approach:

- ✅ Parallel Work: 4x faster than serial

- ✅ Clear Ownership: No confusion about who does what

- ✅ Easy Tracking: Progress visible daily

- ✅ Low Risk: Issues isolated to modules

- ✅ Scalable: Can add devs if needed

- ✅ Professional: Real-world software development

### This is How Real Teams Work:

- Google, Facebook, Amazon all use modular development

- Microservices architecture

- Clear interfaces between modules

- Independent deployment

You’re not just building a hackathon project, you’re learning professional software development! 🚀

Now each developer knows EXACTLY what to build, when to integrate, and how to track progress! 💪

Good luck! 🏆